## README
Last Update | 2019-04-22
Author | Stephanie Qian / Jonathan Le / Robert Yee / Dylan Siv / Ian Bonafede
Email
Description | DJ-IRS: Build a music-sharing web application that has a corresponding visualizer
Summary / Requirements | This spreadsheet serves two purposes: (1) for your team to track progress during your sprints, and (2) as a record of what user stories were implemented, in which tasks, and by whom. For (1), if you prefer to use an alternate tool to track progress as you go (e.g., Trello), that is fine. However, for (2), it is critical that you keep the "Product Backlog" and "Archives" up to date, at least at the end of each sprint. Also, note that if the number of estimated points for a story ends up being very inaccurate (i.e., if the user story took much more or much less effort than expected), please update the story points estimate and give a comment explaining the adjustment.
Tabs | Notes
"Product Backlog" | Should be initialized with the user stories and their estimated efforts (i.e., story points)
Depending on the amount of story points, some stories may need to be split into smaller stories
Add "Acceptance Criteria" to each user story by "insert note" to a spreadsheet cell (right click the cell)
"Acceptance Criteria" define what it means to be "Done"
"Task Board" | "To Do" is initialized with tasks defined during the Sprint Planning Meeting (i.e., sprint backlog)
Tasks are expected to have similar sizes, each with a time cost of roughly 3-4 hours
Add "Details" and "Acceptance Criteria" to a task by "insert note" to a spreadsheet cell (right click the cell)
Perform task assignments at the Sprint Planning Meeting
During a sprint, members who become available can pull tasks from the "To Do" list by moving them to "In Progress" and attaching his/her name
Inform your teammates know before you pull a task from "To Do" list
"To Verify" should be pulled by a different team member; This is a good time to perform code review and unit testing
A task in "Done" list should have its verifier's name appended
"Archives" | At the end of a Sprint, finished tasks are moved to "Archives"; Unfinished tasks are moved to the next Sprint Planning Meeting
"Burndown Chart" | At the end of a Sprint, update the "Burndown Chart"
if "Story Points (Remaining)" is above the "Ideal", it would be an indicator for slow progress

## Product Backlog
ID | Story Name | Story (small features) | Story Points | Priority | Comments
1 | Account | As a new user, I would like to create and login to my own account. | 7 | 3 | Includes Profile & Delete
2 | Sharing Music | As a user, I would like to share music between my friends. | 9 | 1
3 | Recommended Music | As a user that wants to find new music, I would like to have a list of recommended songs based on the song I just listened to. | 6 | 11
4 | Autoplay | As a multi-tasking user, I would like the next song to play automatically. | 5 | 7
5 | Favorites | As a user that has preferred songs, I would like to be able to favorite songs so I can access them more easily in the future. | 5 | 10 | Favorites and Playlist has the same main feature
6 | Playlists | As a user, I would like to be able to save songs into custom playlists and access/edit them later on. | 5 | 9
7 | History | As a user that wants to look back at previous songs I listened to, I would like a way to view my listening history for future references. | 3 | 8
8 | Friends | As a user, I would like to have a list of friends stored on my account. | 6 | 5
9 | Syncing | As a user with friends, I would like to sync my current song to what they are listening to (essentially streaming the music to them in real time). | 9 | 2 | Syncing, Group Queue, and Autoplay fall under the same realm
10 | Messaging | As a user with friends, I would like to be able to message my friends. | 7 | 6
11 | Visualizer | As a user listening to music, I would like to experience a visualizer along with the music. | 8 | 12 | If there's enough time at the end
12 | Group Queue | As a user that listens with friends often, my friends and I often want to play different songs without interrupting what is currently playing. | 6 | 4
| Total |  | 76

## Task Board
To Do (Sprint Backlog) | In Progress | Testing | Done
Task 1: Initial Setup
Task 2: Basic User Account
Task 3: Share Music
Task 4: Add Music
Task 5: Messaging
Task 6: Autoplay
Task 7: Playlist, Favorites
Task 8: History
Task 9: Recommended Music
Task 10: Visualizer [Only if enough time]
Task 11: Extra Features/Bug Fixes
Sprint 1
Sprint 2
Sprint 3

## Archives
Sprint ID | Scrum Master | Tasks Completed
.. | .. | ..

## Burndown Chart
Sprint ID | Story Points (Total) | Story Points (Completed) | Story Points (Accumulated) | Story Points (Remaining) | Ideal
0 | 35 | 0 | 0 | 35 | 35
1 | 35 | 2 | 2 | 33 | 30.625
2 | 36 | 3 | 5 | 31 | 26.25